## Sheet1
Risk | Cause | Effect/Impact
Compromised data | Pushing passwords on to a public repository on GitHub | Data can be manipulated by people who are not autherisd to do so (hackers)
Poor productivity |  | Can result in parts of the project being incomplete.
Unstable internet connection | Due to heavy internet usage by members of my family | Can result in parts of the project not being completed on time. Can also result in me not receiving the help I need from the trainers.
Covid-19 | This project will be carried out during a pandemic where chances of catching the virus will be extremely high | The illness can severly impact my abilty to work.
Inadequate testing | This may be due to insufficient unite testing or not closly adhering to the TDD methodology | This will result is some aspects of the software behaving unexpectadly.